## Course Build Tracker
FIDEO GLOBAL ¦ Course Build Tracker — updated 25 Jul 2026
Course Name | Priority | 1 Data Gathering | 2 Overview & Timeframes | 3 Create Script | 4 On-Demand Content | 5 Activities | 6 Academy Setup | 7 Timetables | 8 Tutor Recording | 9 QA | 10 Go-Live | Go-Live Target | Notes / Blockers / Owner
IFR Training Programme - Part I | HIGH | Complete | Complete | Complete | Complete | Complete | In Progress | WIP | WIP | TBC | TBC | Oct-26 | OG's 14 IFR videos completing EOD tomorrow — mostly prepped. QA needed from owner side. Pending UoL partnership agreement. Launch Oct 26. Owner: AQ/OM
IFR Training Programme - Part II | HIGH | Complete | Complete | WIP → Review | WIP | WIP | WIP | WIP | TBC | TBC | TBC | Oct-26 | Template and 2 Blockchain videos — completing EOD Tuesday (aiming Monday). Pending UoL partnership agreement. Launch Oct 26. Owner: AQ/OM
Cyber Resilience Act - #01 (Crab Nebula) | HIGH | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | TBC | End Aug 2026 | Stage 5 QA — AQ conducting final content check this week. Then uploading to Academy. Pending Crab Nebula review — ready to launch end August. Owner: AQ/OM
Solance Training Programme | HIGH | Complete | TBC | TBC | WIP | WIP | TBC | TBC | TBC | TBC | TBC | Mid Sep 2026 | Stage 4/5 — Layer 4 complete. Layer 1 digital lessons due mid September. AQ reviewing scope — prepped by Wed/Thu, anything outstanding by Friday. Waiting on content from Solance. Owner: AQ/OM
Financial & Digital Literacy | HIGH | Complete | Complete | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | Q4 2026 | Stage 4 not started. On track Q4. Owner: AQ/OM
PFAI Training Programme | HIGH | Complete | Complete | WIP | [7 empty] | End Sep 2026 | Stage 2/3 started. End September — waiting contract with PFA. PFAI confirmed with/without FIFPRO funding. Owner: AQ
Analytics Institute - EirGrid | HIGH | Proposal Submitted | Complete | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC | Stage 3 not started — waiting AI feedback. 15 modules x 15 mins. 4-6 week build when contract signed. Owner: AQ
Fincrime (previously AMLi Chapters) | HIGH | Complete | Complete | Complete | Complete | WIP | WIP | WIP |  |  |  | End Aug 2026 | Ben updating — editing, downloading, reuploading and chaptering in progress. Major editing done. Pre-records TBC and marketing required. Launching end August. Owner: AQ/OM/Ben
Malta - AML | MEDIUM |  |  |  | TBC | TBC | TBC | TBC | TBC | TBC | TBC | End Aug 2026* | Stage 4 not started — awaiting sign off & contract. End August provisional. AQ to nudge. Owner: AQ/OM
CU - AML | HIGH | Proposal Submitted | Complete | Complete | [7 empty] | — | —
Stablecoins / Crypto / MiCA | MEDIUM | Complete | TBC | TBC | [7 empty] | Under review | Stage 3 not started — under review. Owner: AQ
Web3 | MEDIUM | Complete | TBC | TBC | [7 empty] | 31 Aug 2026* | AQ moving back into Blockchain and building ECI academy after Solance. Need to define route to market. Owner: AQ/OM
Resilience (DORA) | MEDIUM | Complete | TBC | TBC | [7 empty] | Under review | Stage 3 not started — under review. Owner: AQ
CU - STR | MEDIUM |  |  |  | TBC | TBC | TBC | TBC | TBC | TBC | TBC | End Jul 2026* | Stage 4 not started — waiting on sign off & contract. Proposal sent. Owner: AQ/OM
Gambling Compliance | MEDIUM | Scoping | [9 empty] | End Jul 2026* | Stage 1 started — waiting on sign off & contract. Owner: AQ
India On Demand Courses - #1 & #2 | HIGH | Complete | Complete | Complete | WIP | WIP | [5 empty] | End Aug 2026 | Stage 4/5 — AQ/OM started on production on #1 & #2. End August. Owner: AQ/OM
India On Demand Courses - #3 & #4 | HIGH |  | Started | [8 empty] | End Sep 2026 | Stage 2 not started — waiting approval. End September. Owner: AQ/OM
AMLi Specialised Pathways | LOW | Complete | TBC | [8 empty] | TBC | Stage 2 TBC. Owner: AQ
TCD Short Course | LOW |  |  | Started | [7 empty] | TBC | Stage 3 — proposal sent. Owner: AQ
Analytics Institute - Shorts
AML RS | HIGH | [10 empty] | Under review | Stage 1 — AQ working with AML RS on proposal. Owner: AQ
Charity Intelligence | HIGH | [10 empty] | MOA TBC | Stage 1 — Post MOA, target pilot for Academy. Owner: AQ
* Provisional dates — subject to contract signing. ⚠ Stagger build start dates — 4 concurrent builds is not workable. Analytics Institute now named EirGrid.

## Projects
FIDEO GLOBAL ¦ Project Register
Projects at pre-pipeline stage — update before weekly ops meeting. These move to Pre-Build Sheet once approved.
Project Name | Description | Status | Lead | Next Step | Target Date | Notes
ECI — Erasmus | Erasmus-funded content build via ECI Malta. 9 modules commissioned — ECI pay FIDEO to build. | In Progress |  | Progress ECI approval process; advance contract execution | Q1 2027 | Linked to Crab Nebula CPD. Largest single EdTech opportunity. Handle carefully.
EU-LATAM Fintech Corridor | Fintech regulatory training programme bridging EU and Latin American markets. | In Progress |  | Follow up post meeting; progress to contract. Surveying pilot underway. | Q4 2026 | Estonians sourcing funding. Early stage.
Anthropic Engineers | AI/engineering training programme in partnership with Anthropic. | Not Started
CBI Tender | Central Bank of Ireland tender opportunity for regulatory training. | Not Started |  | Qualify scope and level of interest | TBD | Contact: Eoin Fitzgerald. Revenue unquantified.
Connector |  | Not Started
ETB Tender | Education and Training Boards tender for public sector training delivery. Consortium bid via Innerpharma. | In Progress |  | Track tender publication; prepare bid response | Q1 2027 | Irish public sector. Tender-dependent. €100k opportunity.
Yellow cells need to be completed. Projects move to the Pre-Build Sheet once approved to build.